## Sheet1
% Complete | Task Mode | Task Name | Start | Finish | Baseline Finish | Baseline Work | Actual Work | Baseline Cost | Actual Cost | Cost Variance
49% | Auto Scheduled | Fleet System 2025 - Delivery Schedule | Mon 26/05/25 | Tue 3/03/26 | Thu 11/12/25 | 3,411.93 hrs | 1,174.98 hrs | 265735.2 | 114124.77 | 26236.61
100% | Auto Scheduled | Planning | Mon 26/05/25 | Fri 6/06/25 | Tue 10/06/25 | 209 hrs | 184 hrs | 44209.95 | 42638 | -1571.95
46% | Auto Scheduled | Delivery | Tue 10/06/25 | Tue 3/03/26 | Thu 11/12/25 | 3,202.93 hrs | 990.98 hrs | 221525.25 | 71486.77 | 27808.56
100% | Auto Scheduled | Design | Tue 10/06/25 | Fri 22/08/25 | Thu 26/06/25 | 332.13 hrs | 379.97 hrs | 24318.15 | 26823.85 | 2505.7
74% | Auto Scheduled | Build | Mon 16/06/25 | Tue 30/09/25 | Tue 22/07/25 | 255.2 hrs | 460.2 hrs | 21588.4 | 36309.1 | 27320.1
100% | Auto Scheduled | PM (moved from BUILD #30) | Mon 16/06/25 | Fri 12/09/25 | Tue 22/07/25 | 45.2 hrs | 138.5 hrs | 4158.4 | 12742 | 8583.6
100% | Auto Scheduled | RC UI Review / Redesign | Mon 30/06/25 | Mon 28/07/25 | NA | 0 hrs | 62 hrs | 0 | 4402 | 4402
100% | Auto Scheduled | RC Build support | Mon 21/07/25 | Fri 5/09/25 | NA | 0 hrs | 201.5 hrs | 0 | 14334.5 | 14334.5
36% | Auto Scheduled | Rent Centric | Mon 14/07/25 | Tue 30/09/25 | Tue 1/07/25 | 0 hrs | 0 hrs | 0 | 0 | 0
58% | Auto Scheduled | Rent Centric Reservations | Mon 14/07/25 | Mon 4/08/25 | Wed 18/06/25 | 0 hrs | 0 hrs | 0 | 0 | 0
55% | Auto Scheduled | Rent Centric Delivery Logistics | Fri 18/07/25 | Tue 12/08/25 | Mon 23/06/25 | 0 hrs | 0 hrs | 0 | 0 | 0
42% | Auto Scheduled | Rent Centric Rentals | Wed 13/08/25 | Mon 25/08/25 | Wed 25/06/25 | 0 hrs | 0 hrs | 0 | 0 | 0
0% | Auto Scheduled | Rent Centric Invoicing | Wed 27/08/25 | Wed 3/09/25 | Wed 25/06/25 | 0 hrs | 0 hrs | 0 | 0 | 0
0% | Auto Scheduled | Rent Centric Exception Mgmt. (Cancellation, Termination, Exchange) | Thu 11/09/25 | Wed 17/09/25 | Tue 1/07/25 | 0 hrs | 0 hrs | 0 | 0 | 0
0% | Auto Scheduled | Rent Centric Mobile Application | Thu 18/09/25 | Mon 22/09/25 | Thu 26/06/25 | 0 hrs | 0 hrs | 0 | 0 | 0
0% | Auto Scheduled | Rent Centric Dashboards | Thu 25/09/25 | Tue 30/09/25 | Mon 30/06/25 | 0 hrs | 0 hrs | 0 | 0 | 0
32% | Auto Scheduled | Integration | Tue 17/06/25 | Thu 18/09/25 | Tue 22/07/25 | 210 hrs | 58.2 hrs | 17430 | 4830.6 | 0
100% | Auto Scheduled | Create Reservation | Tue 17/06/25 | Thu 7/08/25 | Mon 23/06/25 | 40 hrs | 40 hrs | 3320 | 3320 | 0
20% | Auto Scheduled | General | Wed 16/07/25 | Fri 8/08/25 | Tue 24/06/25 | 10 hrs | 2 hrs | 830 | 166 | 0
20% | Auto Scheduled | Rates/Pricing | Fri 18/07/25 | Tue 26/08/25 | Thu 26/06/25 | 12 hrs | 2.4 hrs | 996 | 199.2 | 0
0% | Auto Scheduled | Retrieve Updates | Tue 26/08/25 | Tue 9/09/25 | Thu 10/07/25 | 79 hrs | 0 hrs | 6557 | 0 | 0
20% | Auto Scheduled | Update Rental | Mon 4/08/25 | Fri 12/09/25 | Tue 15/07/25 | 29 hrs | 5.8 hrs | 2407 | 481.4 | 0
20% | Auto Scheduled | Update Reservation | Fri 8/08/25 | Thu 18/09/25 | Tue 22/07/25 | 40 hrs | 8 hrs | 3320 | 664 | 0
42% | Auto Scheduled | Change Management | Thu 26/06/25 | Wed 22/10/25 | Fri 1/08/25 | 333.78 hrs | 147.64 hrs | 19465.76 | 8106.56 | 5660.5
0% | Auto Scheduled | PM (moved from Change Mgmt. #48) | Thu 26/06/25 | Fri 1/08/25 | Fri 1/08/25 | 41.78 hrs | 0 hrs | 3843.76 | 0 | 0
61% | Auto Scheduled | Develop Support & Training Materials | Mon 30/06/25 | Tue 14/10/25 | Mon 14/07/25 | 192 hrs | 147.64 hrs | 10272 | 8106.56 | 8260.5
80% | Auto Scheduled | Onboarding a Customer | Mon 30/06/25 | Fri 26/09/25 | Tue 1/07/25 | 12 hrs | 122.6 hrs | 660 | 6731 | 9118
50% | Auto Scheduled | Logistics Management | Mon 7/07/25 | Wed 24/09/25 | Tue 8/07/25 | 36 hrs | 6.04 hrs | 1980 | 332.06 | 0
17% | Auto Scheduled | Delivering a Hire Vehicle | Fri 8/08/25 | Tue 30/09/25 | Fri 11/07/25 | 24 hrs | 9 hrs | 1320 | 495 | 0
0% | Auto Scheduled | Corporate Hire | Tue 30/09/25 | Wed 1/10/25 | Mon 14/07/25 | 12 hrs | 0 hrs | 660 | 0 | 0
97% | Auto Scheduled | Fleet Management | Mon 30/06/25 | Mon 6/10/25 | Mon 30/06/25 | 12 hrs | 10 hrs | 660 | 548.5 | 26
0% | Auto Scheduled | Returning a Vehicle | Wed 1/10/25 | Mon 6/10/25 | Tue 1/07/25 | 24 hrs | 0 hrs | 1248 | 0 | -1099.5
0% | Auto Scheduled | Exchanging a Vehicle | Wed 1/10/25 | Mon 6/10/25 | Fri 4/07/25 | 24 hrs | 0 hrs | 1248 | 0 | 72
0% | Auto Scheduled | Rates | Mon 6/10/25 | Wed 8/10/25 | Tue 8/07/25 | 12 hrs | 0 hrs | 624 | 0 | 36
0% | Auto Scheduled | Invoicing a Hire | Wed 8/10/25 | Thu 9/10/25 | Wed 9/07/25 | 12 hrs | 0 hrs | 624 | 0 | 36
0% | Auto Scheduled | System Integration | Thu 9/10/25 | Mon 13/10/25 | Fri 11/07/25 | 12 hrs | 0 hrs | 624 | 0 | 36
0% | Auto Scheduled | Claims | Mon 13/10/25 | Tue 14/10/25 | Mon 14/07/25 | 12 hrs | 0 hrs | 624 | 0 | 36
0% | Auto Scheduled | Review & Finalise Support & Training Materials | Tue 14/10/25 | Wed 22/10/25 | Fri 1/08/25 | 100 hrs | 0 hrs | 5350 | 0 | -2600
0% | Auto Scheduled | Stakeholder Review / Feedback | Tue 14/10/25 | Mon 20/10/25 | Tue 29/07/25 | 63 hrs | 0 hrs | 3370.5 | 0 | -1638
0% | Auto Scheduled | Finalise & Approve | Mon 20/10/25 | Wed 22/10/25 | Fri 1/08/25 | 37 hrs | 0 hrs | 1979.5 | 0 | -962
10% | Auto Scheduled | QA Testing | Fri 27/06/25 | Tue 28/10/25 | Fri 22/08/25 | 699.42 hrs | 3.17 hrs | 51154.14 | 247.26 | -7677.74
0% | Auto Scheduled | PM (moved from QA Testing #66) | Fri 27/06/25 | Fri 22/08/25 | Fri 22/08/25 | 64.42 hrs | 0 hrs | 5926.64 | 0 | 0
19% | Auto Scheduled | Test Case Development | Mon 30/06/25 | Mon 22/09/25 | Thu 24/07/25 | 315 hrs | 3.17 hrs | 23467.5 | 247.26 | -7677.74
27% | Auto Scheduled | Test Case Development (Broken Down) | Fri 29/08/25 | Fri 26/09/25 | NA | 0 hrs | 0 hrs | 0 | 0 | 0
100% | Auto Scheduled | Fleet - Registration / Rentals & Reservation | Fri 29/08/25 | Fri 5/09/25 | NA | 0 hrs | 0 hrs | 0 | 0 | 0
0% | Auto Scheduled | Delivery Logistics | Mon 8/09/25 | Tue 9/09/25 | NA | 0 hrs | 0 hrs | 0 | 0 | 0
0% | Auto Scheduled | Invoicing & Pricing | Tue 9/09/25 | Mon 15/09/25 | NA | 0 hrs | 0 hrs | 0 | 0 | 0
0% | Auto Scheduled | Fleet - Servicing / Issues & Damages | Mon 15/09/25 | Thu 18/09/25 | NA | 0 hrs | 0 hrs | 0 | 0 | 0
0% | Auto Scheduled | Fleet - Miscellaneous | Thu 18/09/25 | Fri 19/09/25 | NA | 0 hrs | 0 hrs | 0 | 0 | 0
0% | Auto Scheduled | Fleet - Vehicle Details / Configuration / Integration | Mon 22/09/25 | Wed 24/09/25 | NA | 0 hrs | 0 hrs | 0 | 0 | 0
0% | Auto Scheduled | General | Wed 24/09/25 | Fri 26/09/25 | NA | 0 hrs | 0 hrs | 0 | 0 | 0
0% | Auto Scheduled | Test Case Execution + Defect Mgmt. | Wed 1/10/25 | Tue 28/10/25 | Fri 22/08/25 | 320 hrs | 0 hrs | 21760 | 0 | 0
0% | Auto Scheduled | Test Cycle 1 | Wed 1/10/25 | Tue 14/10/25 | Thu 7/08/25 | 160 hrs | 0 hrs | 11920 | 0 | 0
0% | Auto Scheduled | Test Cycle 2 | Wed 15/10/25 | Tue 21/10/25 | Thu 14/08/25 | 80 hrs | 0 hrs | 4920 | 0 | 0
0% | Auto Scheduled | Test Cycle 3 | Wed 22/10/25 | Tue 28/10/25 | Fri 22/08/25 | 80 hrs | 0 hrs | 4920 | 0 | 0
0% | Auto Scheduled | Training & Rollout | Wed 22/10/25 | Tue 3/03/26 | Thu 11/12/25 | 1,582.4 hrs | 0 hrs | 104998.8 | 0 | 0